GBNDPWG Draft Programme of Work
2016
· April-May
Analysis of Household and Businesses Questionnaires.

· May 20

WG Meeting 4 (WC Link Officer in attendance).

· By End May
Formulate Outline Vision, Objectives, areas of Evidence-taking for and composition of Sub-Groups.

· June-Sept
Evidence-taking, including occasional public tables outside Shop and Post        Office
· Late August
Further WG meeting to check progress.

· Oct 8th

Village Hall Open Day for GBNDP explaining progress and getting residents’ reactions.

· Late Sept
Further WG meeting to confirm NDP route and discuss its main threads.

· Early October
Apply to WC Neighbourhood Area approval. Start developing NDP.
· Mid-Nov
WC approval of Neighbourhood Area.

· Dec
Further article in Parish News about NDP progress, and village hall meeting, feedback request to residents.

2017
· Jan/Feb
Period of consultation.

· March/April
Finalise Plan.

· Early May
Submit Plan to WC.

· June
WC reaction.

· July
Independent examination.

· September
Referendum.

· October
Plan approved by PC.

· By December
Plan approved by WC.  NDPWG disbanded. 
