## Flood_Actions
Location Ref | Location | Date | Flood Issue | Action Description | Asset Owner | Actions Required | Status | Action Update | Actionee | Action Date Update Status | Maintenance Schedule e.g Yearly, Quarterly, Half Yearly | Maintenance Status | Date of Next Maintenance Check
| The Knapp | 2012-10-20 | Houses in the Knapp were flooded by sewage from Thames Water | Investigate and provide findings and action report | Thames Water - only foul sewage system |  | Open | Thames Water in village week of 9 Nov. Awaiting findings. Thames Water creating flood model for Great Bedwyn. Jenny Elliott is Thames water contact. Takes 3 months for analysis. Telemetry was added but did not give adequate data after heavy rain in July. More telemtry added. Need to wait for next heavy rainfall to get findings. Danny chasing Thames Water for formal update to put in Nov edition of Parish news | Thames Water | 2013-09-30
IFH74008 - MHG74007/DSNP226-D009A | Back Lane Allotment Culvert | 2012-10-20 | Water from fields overwhelmed the drainage system causing flooding through homes and gardens | Build up headwall & improve grill to stop debris getting in | Bedwyn Parish Council | Establish Regular Maintenance schedule | Open | Agreed that Parish council will maintain. Need clarification on how often it should be maintained. Suggestion from independent surveyor to build up headwall and improve grill to stop debris getting in. Will Wiltshire Council fund this suggestion? WC will need to look at grill and head wall and assess this requirement. Wiltshire council agree in principle and can provide sloping grill and instructions. Rather than wall it would be concrete sandbag. Parish Council will find someone to fit it. Grill takes 4-6 weeks to order. Need to get approval from Ramsbury estates. | Wiltshire Council/Parish Council | 2013-09-25 | Carry out inspection once every 6 months and debris to be removed when found. Maintenance schedule should be adjusted to match the need the first couple of inspections should highlight what this is. |  | 2013-05-01
MHG74007/DSNP226-D009A | Back Lane Drain | 2012-10-20 | The drain gets blocked with leaves and debris if not clear water does not flow into pipes under Langstrath House |  | Bedwyn Parish Council | Establish Regular Maintenance schedule | Closed | Agreed that Parish council will maintain. Need clarification on how often if should be maintained. Every 6 months. Check large bush near it. Should this be removed? Anna and Meriel to review and give an opinion. Meriel cut back bush and is watching regularly | Parish Council | 2012-11-15 | check once every 6 months and debris to be removed when found. Cut back surrounding vegitation yearly. Should be adjusted to match the need. |  | 2013-05-01
More accurate location required | Drainage system at north end of Church Street | 2012-10-20 | Causes flooding in Church Street if drains not kept clean | Establish Regular Maintenance schedule | Wiltshire Council - only surface water drains under the highway | Establish Regular Maintenance schedule. | Maintenance | What is agreed maintenance schedule? |  |  | Wiltshire Council currently have a yearly schedule under which gullies in Church street and forest road are cleaned. | On Maintenance Schedule. Transferring from Paul Bolland to Kristian Price | 2013-09-01
| Drains/pipes under Langstrath House | 2012-10-20 | Undersized pipes prevents surface water entering drainage system | Survey of pipes | Owner of Langstrath House | Work to improve pipes | Open | Report says pipes are inadequately sized. Need option from Mouchel report. Expected early December. Catchment flow completed but no analysis of specific pipe sizes. Danny believes if we can stop the water upstream current pipe sizes may be adequate. Mouchel are now Atkins. Danny will chase Atkins for recommendations on bund size. Received report. Awaiting Defra funding to enlarge. | Wiltshire Council | 2013-09-25
Bottom of Langstrath House Garden | Is this seperate to the underground drainage system? More information about the 'wall openings' required. Currently unaware that this was part of the drainage system as underground SW pipes travel from Langstrath House to the Surgery... Wall openings between Langsrath house and surgery | 2012-10-20 | Wall openings are not large enough to allow water to drain away effectively | Increase size of wall openings | M Larkin | Increased wall opening to metre high | Open | Need agreement from surgery who feels that downstream pipes are already at capacity. Wiltshire Council agree sounds good idea in principle but can't give guarantee on whether drains would be adversely affected. Meriel to ask again. Mail sent 30 Sep | Larkin/Fletcher | 2013-09-25
| Brick culvert under surgery | 2012-10-20 | Undersized prevents surface water entering drainage system | Survey of culvert | Owner of surgery | Work to improve culvert | Open | Awaiting findings from Wiltshire Council. Culvert has been cleaned and debris and stones removed by jetting. No debris fell down after cleaning so culvert deemed currently serviceable. Danny reviewing with Christian week of 30 Sep | Wiltshire Council | 2013-09-25 | Wiltshire council to review after Kristian takes over from Paul Bolland and put it under regular maintenance schedule | Planned
CP83003/DSNP226-D009A | Granary Road | 2012-10-20 | Reduced capacity of 300mm pipe causes surcharging of water | Survey of pipes | Man hole cover Thompson (No. 11) St Mary's Field Mgt co. | Work to improve pipes/ or control flows | Open | Wiltshire Council advised outfall was blocked and has now been cleared. Danny to confirm if pipe capacity is enough. John to confirm if this is still an issue since clearing. John confirmed he has seen no leakage. Concern from members that larger pipes are going into such a small pipe. John checked with St Mary's field management company. They are amenable to part funding change of pipe. John is concerned pipe is of clay and of weak construction. Awaiting Defra funding decision which would replace pipe | Wiltshire Council/Thompson | 2013-09-25
MA675 | 7 Manor Road | 2012-11-15 | Sewage flowing into front garden and main manhole (MA675) |  | Thames Water - of foul sewage system |  | Open | Wiltshire Council to advise Thames Water of this issue. Manhole cover MA675. Will be covered by Thames Water report. Danny to make sure Thames Water are aware. Part of Thames Water analysis | Wiltshire Council/Thames Water | 2013-09-25
| Ditches at rear of burden several | 2012-10-20 | Ditches have fallen into disrepair and feed water to water meadow | Re-instate ditches | Bedwyn Parish Council | Cut off ditch behind houses north of Burdens Several Ditch running east down lane between 58 Church St and Burdens - agree Ditch between 42 & 43 Church Street - this is no longer a ditch it was piped by house owners and is the responsibility of the home owners. see the line 12 below. | Open | Agreed that Parish council will maintain. Need clarification on how often it should be maintained Right of waylease access agreed with Carter Jonas. Currently there are crops in the field that need to harvest before work can be done. Contacted Gordon Stone to confirm. Due to amount of water crop is already dead around ditch so why does this have to wait until July. Action. Danny to discuss with Carter Jonas. No longer Cartner Jonas now Ramsbury estates. Will de done in line with bund work at top of Church Street including digging of ditch | Wiltshire Council | 2013-09-25 | Checks of ditches and flow controls every 6 months possibly more oftern in the winter months. Ditches to be cleared annually or biannually depending on silt and vegitation build up.
MH59011 | Buried Chamber | 2012-10-20 | Connects to silted up culvert which connects to MH59011 to JN59004 gives gap in drainage system | Clean silted up culvert | Flecher | Asset owner thinks this is OK. Wiltshire need to confirm if work is required. | Open | As chamber is buried Danny needs to request Atkins to come and survey and jet this specific chamber. Takes a long time to organize. It is not a buried chamber it is a filled in pipe. There is a manhole cover next to it. Trever to show Danny when his visits in March to ascertain what to do. Concern that current proposal to flow down ditch into this pipe will cause flooding to other properties. Reinvestigate buried chamber between 42 and 43 as concern there is a missing section | Wiltshire Council | 2013-09-25
OFH69003/69001 | Water meadow south of Church Street | 2012-10-20 | Multiple irrigation ditches that receive flow from the highway drainage system at the southern end of Church Street | Establish Regular Maintenance schedule | Ramsbury Estates/Gordon Stone | Establish Regular Maintenance schedule | Open | land owned by Ramsbury estates. Regular maintenance is required to keep irrigation ditches working effectively. Awaiting confirmation from Gordon Stone when work will be done. 12 Feb. Wiltshire council proposed counter proposal for tenant farmer to apply for Defra funding to turn back into a water meadow. Danny to chase if they will pursue this. If not back to agreeing a date for clearing. | Wiltshire Council | 2013-03-31 | biannually clear vegitation from outfalls and ensure irrigation ditches are kept clear of silt deposits and any other obstruction that prevents the flow of water.
| Culverts under railway and outfalls into the River Dun | 2012-10-20 | Not working well | Survey of pipes and outfalls | Network Rail | clear outfalls and culverts where required | Open | Awaiting response from Wiltshire Council as to whether they have been able to meet with Network rail. Network rail confirmed no works until next financial year. Some vegetatian clearing has been done. Danny to chase on date for works now we are entering new financial year. Danny advised work has been done. | Wiltshire Council | 2013-09-25 | Need to establish watcher to check regularly for further maintenance
CP62003/71003 | Piped system near church | 2012-10-20 | Discharges water to River Dun | Survey of pipes | Ramsbury Estates/Gordon Stone | awaiting survey results | Closed | Wiltshire Council to confirm they are asset owner and if they plan work to improve these pipes - Ramsbury Estates/gordon stone are the asset owner. Danny to bring this up for discussio with Ramsbury Estates/Gordon Stone. Received survey results and working OK. | Wiltshire Council | 2013-09-25
| Field behind upper Church Street | 2012-10-20 | Houses on right of Church Street as driving out of village towards Crofton get flooded by pools forming in the farm fields behind the houses | Re-establish ditch/bund | Ramsbury Estates/Gordon Stone |  |  | Bund dug by Gordon Stone in Autumn 2013. Effective in January 2014 floods. Check effectiveness and if additional measures from DEFRA funding | Gordon Stone/Ramsbury Estates | 2014-03-01
| Field behind allotments | 2012-10-20 | There is no ditch or bund to delay water in extreme flooding | Re-establish ditch/bund | Ramsbury Estates/Gordon Stone | Re-establish ditch/bund | Open | Wiltshire council are willing to do the work. Parish council will maintain. Flow analysis from Mouchel completed. Size of bund restricted to available piece of field to build it but will contain a drainage pipe to slow down the flow. Can't be built until crops in field have been harvested. Danny to chase date when works can occur. Due to change of land ownership now awaiting approval from Ramsbury Estates. Ramsbury Estates proposed to investigate controlling water further up fields in land leased by Forestry commission. Promised update within 10 days | Wiltshire Council | 2013-09-25 | check once every 6 months to ensure pipe is clear and structure is sound (more regular checks recommended during winter time). Maintenance schedule should be adjusted to match the need.
| Allotments | 2012-10-20 | Get flooded from farm fields behind | install delay weirs in the ditch crossing the allotments - not required | Parish Council rents from Ramsbury Estates |  | Closed | Awaiting findings of Wiltshire council meeting with Ramsbury Estates. Will delay weirs be installed? |  | 2012-11-27 | not required. Piped bund considered suitable.
| Cricket pitch | 2012-10-20 | Lack of drainage causes flooding down Frog Lane and to Wharf property | Find resolution to drainage issue | Cricket club | Drainage options for this catchment are being reassesed | Open | Wiltshire council has discussed with landowner. Awaiting analysis on a number of options. Thames Water looking to add dry wells to pumping station which will give greater capacity to deal with surface water. Danny has asked for Atkins for additional calculations to identify if ditches can be dug to help drain water. | Wiltshire Council | 2013-09-25
D012A/MH3-MH8 | The Wharf | 2012-10-20 | Drainage system blocked restricting the ability to conveyance large amounts of water into the Canal Siphon - MH3-MH8 replaced a ditch that provided additional storage capacity . The pipes are clear and in good condition but conveyance and storage ability is restricted by the smaller pipes that connect to them. | Establish Regular Maintenance schedule | Owners of the Wharf - Mr and Mrs Bond | Establish Regular Maintenance schedule | Open | What is agreed maintenance schedule? | Bond | 2012-01-31
GY1b/c-MH8 | The Wharf | 2012-10-20 | Storage capacity of pipes is less than that of ditch - No, MH8 - MH3 is the ditch that has been replaced. These smaller pipes restrict the rate at which surface water can enter MH8-MH3 that replaced the ditch. | Review upgrading of pipes | The Bonds - on their land, need to establish responsibility for gullies on Frog lane |  | Open | Pipes need to be flushed out can't be done until water meadow exit is dealt with - GY1 - MH3 pipes are clear no flushing is required. MH2 - MH5 contains silt. Suggest if outfall is sufficient to clear but need permission from Martin Rhodes | Bond | 2012-01-31
| Siphon under canal | 2012-10-20 | Partially blocked by silt | Establish Regular Maintenance schedule | Canals Trust | Establish Regular Maintenance schedule - canals trust inspect this every 20yrs, effective drainage will ensure this remains clear of silt and maintenance should not be required | Maintenance | Canals trust analyzed and said it is not blocked. What is Wiltshire Council Opinion. There is a small amount of silt compare to size of siphon. Does not pose a problem to the conveyance of water currently. |  | 2013-05-31 |  | Review once other areas sorted, It may be beneficial for this assets to be checked for blockages and siltation more regularly by a member of the FWG. Suggest Bonds | 2017 by Canals trust
| Ditch from canal siphon to River Dun | 2012-10-20 | Blocked with silt and overgrown | Establish Regular Maintenance schedule | Martin Rhodes | Establish Regular Maintenance schedule | Open | Wiltshire council in discussions with land owner. Has this meeting occured, what is outcome? - Wiltshire Council have made Mr Rhodes aware of his responsibility to clear this ditch and are taking action to ensure it will be cleared. Hoping ditch will be cleared before christmas. Work was done at Christmas. Wiltshire council legal chasing to set precendence to put this under regular maintenance | Wiltshire Council | 2013-03-31 | Ditch to be cleared annually during Autumn/early Winter. |  | Autumn 2013
Boundary of last house (Mr & Mrs Bailey SN8 3LP) on Forest Hill, RHS direction to Marlborough | Drain to Tyle Field from Forest hill | 2012-10-20 | Cut off drain is blocked | Clear and extend cut off drain | Wiltshire Council - on highway, Ramsbury Estates on the field | The drain (ditch) runs parallel to the road for about 20 yards before turning towards the field. It then peters out after a few yards, so is of limited use at present. Ramsbury Estates owns fields | Open | Wiltshire council in discussions with land owner. Has this meeting occured, what is outcome. Now Danny is aware he will meet with Carter Jonas/Gordon Stone on this topic | Wiltshire Council | 2013-03-31
| Hatchet Lane | 2012-11-15 | Water is coming from forest and Vines fields and floods across the Bridleway from one field to another and ends up in Burdens SeveralIt is quite clear in 3D that it is not part of existing contour line based flow path that Emma Truran and Danny Everett are working with, which is higher up the lane. It is a separate additional flow that has been directed towards the rear of Burdens Several and joins the contour line based flow path on the way there. This was caused by the previous tenant farmers either side of Hatchet Lane removing the banks each side of the lane to allow for the passage of a combine harvester from one field to another straight across Hatchet Lane, without reference to any authority (as far as I can establish) but purely for their mutual benefit. With the passage of time the situation becomes worse as the flow of water erodes more and more soil. The situation is so bad now that hatchet lane is frequently impassable at this point. It is absolutely essential that this is either restored or at least taken into account in the calculations, failure to do so would be an act of negligence by the Council. Several of the residents in the affected area are extremely concerned about this situation and do not understand why the Council have not made sure that the banks have been reinstated. | Establish Regular Maintenance schedule for Bridleway which has not been maintained for some time so that water channels down Hatchet Lane and ends up in drains - we do not want water to travel down hatchet lane. The natural flow path is as described in column D | Ramsbury Estates/Gordon Stone |  | Open | Wiltshire Council to confirm they are asset owner and whether maintenance is planned - Wiltshire Council PROW team are responsible for maintaining the surface of this path and Ester Daly will be meeting a member of the PC to look into the condition of the path surface. The SW flow route described in column D should be maintained as this is the natural flow route. Wiltshire Council land drainage team are working with the PROW team to ensure that any work required on the paths surface does not have a detrimental effect on the flow path of the surface water. Wiltshire Council to bring up with Cartner Jonas to ask the landowner to re-instate. Danny to chase findings from PROW/Parish council walk. Trevor advised that other amendments have been made to the banks. Awaiting findings from Ramsbury/Forestry commission evaluation | Wiltshire Council | 2013-09-25 | ditches
| River Dun | 2012-11-15 | Will River Dun become flooded if pipe issues are resolved and more water floods into the river - no | Unless river is blocked further down stream by debris river flooding should not occur. | Riperian owners are asset owners. This is non main river and therefore under the jurisdiction of Wiltshire Council, however this does not make then asset owners. | Riperian owner to ensure effectivce conveyance of the River Dun is maintained. | Closed | Wiltshire Council to comment on concern? none |  | N/A
| opposite Jockey Green on the track | 2012-12-14 | Draincover that has been leaking sewage for several months |  | Thames Water | Send an engineer to fix | Closed | Thames Water sent an engineer and we are hoping that the problem is now fixed for the medium to long term | Parish Council | 2012-01-31 |  | Alistair Feakes to monitor and confirm leak fixed
| Outside of ‘The Stores’ | 2013-01-02 | There are three side by side drain covers. However, they sit out of the gully formed between the kerb and the road. This means that the majority of water just passes by and heads into Church Street | I have observed this twice when, on both occasions, a heavy flow of water was flowing down the High Street against the kerb. On both occasions the drains had leaf mulch blocking them but even when I removed this only about 10% of the water went down the drain – the rest headed into Church Street. | Wiltshire Council | These three drain covers need moving snug against the kerb so they can take all of the water. | Open | Make Wiltshire council aware of issue so they can provide assessment as to how best to deal with. Wiltshire council agreed to put larger gully grates and frames. Paul Bolland change job now Kristian. Awaiting date when he will complete the work. | Parish Council | 2013-09-25
Chiropractor surgery Little Bedwyn | Chiropractor surgery Little Bedwyn | 2013-02-12 | Run off from surrounding land has always collected in the corner of the field next to my garden and inthe garden. When there is a lot of heavy rain the flood goes over the lawn and swamps the downpipe pit, thus making my downpipes become " up pipes" Thus flooding the terrace at the back and side of the house. Since I have been here the water has not come in to the house but is barely a couple of inches away. I have so far prevented the water coming in by pumping it out. I have found that if I keep the water in the lake at a safe distance I have some leeway should the heavy rain come down. Drain problem. Downstairs loo backed up and I couldn't use it for a week. This also affected ALL my downstairs drains. I tipped my washing up water into the river and couln't use the washing machine. I limited the use of upstairs loo and used the garden!! Thames water were so busy with their tankers that they forgot about the pumping house that pumps suage from this side of the canal accross the bridge and on to Great Bedwyn suage workds. I even had suage in the manhole on my property. | Wiltshire council to inspect | TBC Thames Water | Maintenance schedule to clear pumping house in Little Bedwyn that pumps to Great Bedwyn | Open | Danny WC and Trevor to investigate on rescheduled walk round with Kristian. | Wiltshire Council | 2013-09-25
| Ditch in allotment | 2013-02-21 | Overflows at the moment | Should the ditch be deeper | ?Ramsbury Estates or Parish Council | Wiltshire council to advise if the ditch should be made any bigger | Open | In discussion with Ramsbury Estates |  | 2013-09-25
Holgate and Pack | Road from Bedwyn to Wilton | 2013-02-21 | Water comes from farm fields behind them. Retained by wall. Knocked a hole in the wall to relieve. Old ditches grown over | Opinion on how to deal with | Owners of land behind Brail Farm, Jos Hosier | Request made to landowner. Trevor to check with Holgate and Pack if work done | Open |  |  | 2013-09-25
Great Bedwyn Station | Drainage grid at Station Entrance | 2013-02-22 | Partially blocked | FGW to get this unblocked | FGW | Parish Council chasing FGW (Karina Nicholson) | Open | Awaiting confirmation from Parish Council date for clearing | FGW
Granary Road | John to confirm | 2013-09-30 | Similar to stores drain is not positioned correctly to catch all rainfall | Relocate drain | Wiltshire council | Add to Kristian maintenance plan | Open |  | Wiltshire Council
Mill Lane | DSNP226/D006. end (or first) house in the village just over the junction and on the road to Crofton on the left hand side | 2013-11-06 | Drain opposite the house and beside the house and field boundary blocked | Clear drains | Wiltshire council | Clear drains. Job created by Kristian Price | Open | Awaiting confirmation drain cleared | Wiltshire Council
| The Old Telephone Exchange, Back Lane | 2014-01-06 | Field on the left of the footpath (beyond the small gate) up the track had a small lake of water which was feeding into the field next to my house (the one with the ponies) and eventually that field was unable to hold it and the only place left for the water to go was into my garden and down towards the house. | Gordon Stone and others dug a small ditch from the field with the lake of water in it across the footpath into the field behind the allotments. This seems to have done the trick for now but it's only a temporary solution. | Ramsbury Estates/Gordon Stone | Investigate more permanent solution in line with works done by Ramsbury Estates | Open

## Other_Actions
Date | Action Description | Actionee | Action Status | Action Update
2012-11-15 | Mouchel findings on flow rates | Mouchel | Closed | Sent to Wiltshire Council
2012-11-15 | Invite Keith Marshall and Anna Ditchburn to be members | Maggi | Closed | Mail sent
2012-11-15 | Floodwatcher for Forest Hill | Tesher | Closed | Patrick Pease
2012-11-15 | Update for Parish News | Rachel | Closed
2012-11-15 | Is land behind Burdens Several leased | Trevor | Closed | N/A superior landlord agreed to do the work
2012-11-15 | Canvas views on extent of flooding at Coster View, Fairfield and Shawgrove | Tesher | Closed | Coster View properties added to at risk
2012-11-15 | Update on Thames Water meeting | Tesher | Open | takes 3 months
2012-11-15 | Create template for individual house owners to complete | Maggi | Open
2013-02-21 | Parish council employee | Roger | Open | Confirm he is in post